STRENGTHENING CONSENSUS-BASED LOCAL WEATHER FORECASTING FOR ENHANCED RESILIENCE (SCLoWFER) IN THE TRI-BORDER AREA OF

BURKINA FASO, COTE D’IVOIRE AND GHANA

A Framework and Tool for Integrating Traditional Knowledge Indicators into Local Weather Forecasting for Climate Resilience in the Context of Human Mobility, Displacement and Conflict in the Tri-Border Area of Burkina Faso, Côte d'Ivoire, and Ghana

A Technical Proposal for A Pilot Project

Submitted to GIZ Nigeria

By

| ADAPTATION CONSORTIUM (ADA) 2nd Floor, The Bazaar Plaza, Biashara Street/ Moi Avenue Street, P.O. Box 40700 - 00100, Nairobi, Kenya Tel: +254 202020198 E: info@adaconsortium.org; www.adaconsortium.org | AND | CES Head-Quarters BL 19 Tessa Street. GW-0797-0112 Greater Accra , Ghana Tel: 0900.123456 Mail: info@ces-global.org |
| --- | --- | --- |

# Table of Contents

Table of Contents	i

List of Figures	ii

Abbreviations and Acronyms	iii

Executive Summary	iv

1	Introduction	1

2	Background information	2

2.1	Context analysis	2

2.1.1	Challenges with community level climate information & weather forecast credibility	2

2.1.2	Challenges of climate change in the West Africa Region	3

2.2	Geographic location:	3

2.2.1	The tri-border area of Burkina Faso, Côte d'Ivoire, and Ghana	3

3	Profile of Implementing Partners - Presentation of the recipient	4

3.1	Adaptation Consortium Registered Trustees	4

3.2	Climate and Environment Services	5

4	Project objective/outcome:	5

4.1.1	The proposed pilot project:	6

4.1.2	Project Objectives	6

5	Expected Results	6

6	Progress and Milestones	7

7	Approach and Methodology: planned activities for the implementation of the measures:	7

7.1	Approach	7

7.1.1	The TILKIT Workshop	8

7.1.2	The tri-border area pilot	8

7.1.3	Monitoring, sharing and learning	8

7.1.4	Dissemination     	8

7.1.5	Project management, coordination and partnership and roles	8

7.2	Methodology	10

8	Criteria for selecting project participants and local stakeholders:	12

9	Sustainability Plan, Exit Strategy and Scaling Roadmap	13

9.1	Sustainability Plan	13

9.2	Exit Strategy	14

9.2.1	Phased Transition to Local Ownership	14

9.3	Replication & Scaling	15

9.3.1	Scaling Roadmap	15

10	Monitoring, evaluation and reporting	15

10.1.1	Project LogFrame	16

10.1.2	Plan of activities/ Work plan/ Work Plan for one year	21

11	Risk and damage limitation	24

12	References:	27

Annexes	28

1 Feedback from the May 20 2025 ECOWAS Meteos (NMHSs) Meeting Pitching	28

# List of Figures

Figure 1: Project site - the tri-border area of Burkina Faso, Cote d’Ivoire and Ghana	4

Figure 2: A graphical representation of the TILKIT workshop model	10

Figure 3: Steps of the TILKIT process	11

List of Tables

Table 1: Project log frame	17

Table 2: Planned activities	21

Table 3: Risk Matrix	24

# Abbreviations and Acronyms

ACMAD 	African Center for Meteorological Applications for Development

ADA 	Adaptation Consortium (an NGO Registered in Kenya)

AGRHYMET 	Regional Climate Centre for West Africa and the Sahel

AICCRA	Accelerating Impacts of CGIAR Climate Research for Africa

ASAP 	Anticipatory Scenario Action Plans

AU 	African Union

CbA 	Community-based Adaptation

CBO 	Community-based Organisation

CES 	Climate and Environment Services (an NGO Registered in Ghana)

CGIAR 	Consultative Group on International Agricultural Research

CIS 	Climate Information Services

CRBi 	Climate Resilient Borderlands Horn of Africa (an NGO in Eastern Africa)

DCF 	Direct Climate Finance (aka: Decentralized Climate Finance in some countries or Devolved Climate Finance in Kenya)

DRM 	Disaster Risk Management (or Drought Risk Management)

DRR 	Disaster Risk Reduction

ECOWAS 	Economic Community of West African States

FARA 	Forum for African Agricultural Research

FGD 	Focus Group Discussions

GESI 	Gender equity and social inclusion

GIS 	Geographic Information Systems

GIZ 	Gesellschaft für Internationale Zusammenarbeit (GIZ) GmbH

IIED 	International Institute for Environment and Development

ITK 	Indigenous Technical Knowledge (aka: Indigenous and Traditional Knowledge)

KMD 	Kenya Meteorological Department

KNUST 	Kwame Nkrumah University of Science and Technology

LLA 	Locally Led Adaptation

PSP	Participatory Scenario Planning (for climate action initiatives in Africa)

SCLoWFER	Strengthening Consensus-based Local Weather Forecasting for Enhanced Resilience

TILKIT 	Traditional, Indigenous and Local Knowledge Indicator Tool (for community climate monitoring and weather forecasting)

ToT 	Training of Trainers

WMO 	World Meteorological Organization

# Executive Summary

Overview: This pilot project proposal, titled "Strengthening Consensus-based Local Weather Forecasting for Enhanced Resilience (SCLoWFER) in the tri-border area of Burkina Faso, Cote D’Ivoire and Ghana," outlines a 12-month initiative (September/October 2025 to September/October 2026). The aim of the project is to enhance climate resilience and reduce climate-induced mobility, displacement, and conflict in the tri-border region. The proposed pilot project, SCLoWFER, jointly developed by the Adaptation Consortium (ADA) and Climate and Environment Services (CES), seeks to enhance climate resilience among vulnerable communities in the tri-border region. The project is intended to pilot a Traditional, Indigenous and Local Knowledge Indicator Tool (TILKIT) to integrate indigenous forecasting with scientific methods, empowering vulnerable communities in West Africa’s tri-border area to anticipate, plan for, and respond to climate-related risks. The initiative targets migration, displacement, and conflict driven by climate variability through community-led weather monitoring, seasonal forecasting, and anticipatory action planning. The initiative pioneers a systematic, community-driven approach to weather forecasting that applicably integrates indigenous knowledge with conventional climate services. This effort aims to reduce climate-induced mobility, displacement, and resource-based conflicts in the region.

Statement of the Problem: Climate change impacts and environmental degradation in the West African Sahel are exacerbating competition for resources in the targeted tri-border area, particularly between farmers and transhumant pastoralists, leading to conflict and displacement. Rising climate variability has exacerbated droughts, disrupted agro-pastoral systems, and intensified conflicts over natural resources. Conventional forecasts struggle to gain legitimacy but are still less trusted or less accessible at the community level. Indigenous and Traditional Knowledge (ITK) of weather prediction, though more trusted by local communities in the past, are increasingly undermined by climatic and environmental change. ITK as currently used lacks a systematic framework, structure, validation, application and integration into formal or conventional forecast systems Current efforts to integrate these knowledge systems have been ad-hoc and inconsistent, often failing to incorporate diverse community voices, including women and youth. The Traditional, Indigenous and Local Knowledge Indicator Tool (TILKIT) framework aims to bridge this gap by offering a practical, sustainable, and gender-responsive approach to co-generate climate knowledge and integrate seasonal weather forecasts. The project aligns with ECOWAS Vision 2050 and AU Agenda 2063, promoting inclusive, gender-responsive, and resilience-building interventions. The pilot will specifically focus on communities in the Ghana side of the tri-border area (the Saru, Kluajon, Kalba and Konfusi), considering cross-border practices for future scaling.

Rationale and Project Objectives: The project deploys TILKIT as a participatory, community-oriented forecasting tool that collects, validates, and integrates indigenous weather indicator outcomes with scientific forecasts. The broad objective is to enhance gender-responsive adaptive capacity, strengthen resilience, and reduce vulnerability in the target communities in the context of human mobility, displacement, and conflict. Specific objectives include:

- Co-development of Climate Services: To co-develop gender-responsive, consensus-based seasonal weather forecasts, user-responsive weather advisories customized to local contexts, and Anticipatory Action Plans (AAPs) for resilience building.

- Information Dissemination: To establish a gender-responsive, inclusive community data collection and dissemination system, climate information dissemination strategy and communication framework that integrates local knowledge.

- Implementation Support: To facilitate and empower local communities and actors, especially women and youth, to self-organize around co-produced climate information and anticipatory action planning, and to support them to implement climate-informed, gender-responsive AAPs.

- Lesson Sharing: To share lessons learned for wider consideration and dialogue to inform future climate information services, and to institutionalize TILKIT into local governance structures, national climate services frameworks, and regional and continental policy processes.

Approach and Methodology

The 12-month pilot will cover one dry period and one rainy season. The project will employ a three-phase approach, with a fourth component for project management:

- Pre-Season or Pre-Workshop Planning: Training of Trainers to mobilise communities to collect TILKIT data for consideration during the workshop

- The TILKIT Workshop: This phase involves adopting TILKIT to co-produce weather forecast scenarios, advisories and Anticipatory Action Plans (AAPs). It emphasizes a "whole-of-society" approach, engaging diverse social groups through Focus Group Discussions (FGDs) to identify and validate both historical and emerging indicators and experiences.

- Tri-border Area Pilot: This phase will pilot the co-produced local weather AAPs on the Ghana side of the tri-border area, evaluating user interaction and benefits, identifying behavioural mechanisms to foster utilization, and co-designing dissemination strategies to raise awareness.

- Monitoring, Feedback, Learning and Sharing: This phase focuses on facilitating community dissemination and monitoring through dedicated local committees, documenting progress and feedback, assessing changes in beneficiary behaviour, and packaging evidence to influence policy reforms. Opportunities for a central digital repository for TILKIT forecasts will be explored. This phase will include promoting data harmonization across conventional and indigenous systems to improve forecast legitimacy and actionability

- Project Management: ADA, as the lead implementer, will be responsible for overall project management, coordination, and reporting, working with CES partners in Ghana for day-to-day responsibilities and site-level oversight.

Target Area: The initial pilot focuses on communities on the Ghanaian side of the tri-border region, involving cross-border populations from Ghana, Burkina Faso and Côte d’Ivoire. Primary participants include settled smallholder farmers, transhumant pastoralists, displaced persons, and local populations of women, youth, and vulnerable community members in the tri-border area. Emphasis is placed on inclusive participation, especially from traditionally marginalized voices.

Key Expected Outputs and Outcomes:

| Outputs | Outcomes |
| --- | --- |
| - Tallied list of indigenous indicators of rainfall and what they signify in terms of local climate and weather - Community-validated local forecasts and weather advisories (early warnings) - Anticipatory action plans to prevent displacement or to cope better with displacement - Dissemination and Communication Plans; Monitoring and reporting plans; Policy dialogue plans, etc. - A scalable TILKIT model for West Africa and Africa - Plans for capacity-building of community committees and intermediaries - Documented lessons, best practices, and policy briefs to influence regional climate resilience strategies | - Reduced livelihood disruptions in the tri-border area - Increased Social Cohesion and cultural resilience in the tri-border area - Reduced climate-related displacement and conflict through increased mutual understanding - Enhanced capacity to understand indigenous knowledge of weather forecasting systems - Increased decentralization of climate services Governance - Learning-based adjustments ensure relevance and long-term usability - Enhanced community ownership and governance of climate information - Increased evidence-based influence for policy reforms |

Sustainability & Scaling: The project will contribute to ECOWAS Climate Strategy and Action Plan (2022–2030) and AU Agenda 2063 objectives, particularly in indigenous indicators, early warning climate services, rainfall forecasts, disaster risk management, and action planning related to mobility. Through phased transition to local ownership, capacity development, institutional embedding and awareness raising, the project aims to evolve TILKIT into a replicable model for Africa-wide adoption. Intended policy integration dialogues under ECOWAS Climate Strategy and Action Plan (2022–2030) and AU Agenda 2063 is expected to position the tool for broader geographic and thematic expansion. The sustainability plan envisions institutionalizing TILKIT across Africa's climate-vulnerable regions as a model for integrating traditional knowledge into formal weather and early warning systems. This will be achieved through:

- Policy Integration: Embedding TILKIT into local governance, climate service systems, and regional policy platforms by collaborating with national meteorological and hydrological agencies.

- Institutional Integration: Anchoring TILKIT within local government and community structures.

- Capacity Development: Training local trainers and community indicator monitoring groups as "TILKIT Champions" to ensure ongoing forecast co-production and action planning at the grassroots level.

- Digital Repository: Exploring the development of an open-access digital platform for TILKIT data.

Implementing Partners:

- Adaptation Consortium (ADA) – Lead implementer (Kenya)

- Climate and Environment Services (CES) – Local implementation partner (Ghana)

Duration: 12-month pilot (Sep/Oct 2025–Sep/Oct 2026)

Funding: Request made to GIZ Nigeria

Conclusion: The initiative marks a transformative step towards anchoring resilience-building in culturally resonant, data-informed community-based weather forecasting systems. The exit strategy emphasizes a phased transition to local ownership, with responsibilities gradually shifting to trained community committees and local governments. Training manuals, data templates, and user guides will be shared to ensure operational continuity, and local organizations will be trained to mobilize funds for continued project activities. The project aims to position TILKIT for broader scale-up through evidence-based engagement, capacity development, and regional advocacy.

# Introduction

Increased climate variability and public insecurity are major drivers of human mobility, influencing migration, displacement and relocation patterns, often leading to resource-use conflict, including cross-border conflicts, impacting livelihoods. Cross-border herder-farmer conflicts in relation to drought, land and water tensions have become widespread in the West African Sahel Region. With increasing number of extreme weather events and increasing cropland expansion due to declining agricultural productivity, local subsistence farmers and seasonally migrating (transhumant) pastoralists increasingly compete for natural resources such as water and vegetation. Such competition has increased in both number and severity, often resulting in resource-based conflicts and violent clashes, leading to forced displacement of communities or population groups. A traditional, indigenous and local knowledge indicator tool (TILKIT) is vouched in this proposal to address some of the problems that lead to human mobility, displacement and conflicts mentioned in the region. TILKIT is a community-based systematic co-generation of climate knowledge and integration of seasonal weather forecasts. Relevant areas of TILKIT contribution will include transdisciplinary approaches, participatory information dissemination and sharing, capacity building, gender-responsive policy advice, especially touching on vulnerable groups such as women and youth, etc.

Developed at the culmination of several participatory scenario planning (PSP) initiatives in Africa, TILKIT aims to strengthen weather forecasting and enhance climate resilience by leveraging indigenous, traditional and local knowledge. The Tool was developed in farming environments but has since been taken through a scoping process in a pastoralist mobility and potential conflict context and found helpful by Maastricht University and the Climate Resilient Borderlands Horn of Africa (CRBi). The scoping was done in Karamoja Pastoralist Cluster in Eastern Africa, comprising Kenya, Uganda, South Sudan and Ethiopia. Similar CbA approaches to climate information services (CIS) has also been found to be more beneficial in the region. An economic valuation of contextualized CIS in Kenya, compared to nationally dispensed CIS, found that households receiving contextualized CIS, specifically local forecasts and advisories, returned consistently higher income levels. A CbA aggregated for agriculture, pastoralism and other livelihoods, also found that contextualized provision is economically viable.

Although indigenous and traditional knowledge (ITK)-based climate information and weather forecast is inbuilt and well-established among many traditional and indigenous communities across the world, a systematic observation and documentation of local weather using ITK indicators in forecasting for organized application has not been attempted in the past. Often there is pressure on practitioners, researchers and stakeholders to collect, preserve, calibrate, validate and adopt ITK indicators to fill gaps left by conventional climate monitoring and weather forecasting to address residual climate risks that that scientific forecasts alone might not cover. However, the initiatives introduced so far to address this problem have been largely project-based, ad hoc and academic, with no clear decision-support tool to move the conversation to a practical and sustainable model, always fizzling out as soon as the project closes. The TILKIT Framework is the first attempt to fill that gap. The TILKIT tool applies traditional/indigenous and local technical knowledge (ITK), riding on the back of transdisciplinary co-production and upscaling to meet the downscaled scientific seasonal forecast at the sub national level. The Framework makes it possible to build a new set of knowledge using a new tool by opening the conversation with the whole community from diverse social groups (male, female, youthful and elderly) to identify emerging indicators and experiences. This approach can support empowerment of women and youth through recognizing and valuing their knowledge and roles as change agents .

# Background information

The TILKIT pilot project directly supports the Economic Community of West African States (ECOWAS) Vision 2050 and the African Union (AU) Agenda 2063 by promoting inclusive, gender-responsive, and resilience-building interventions that strengthen local governance and reduce displacement and fragility.

## Context analysis

### Challenges with community level climate information & weather forecast credibility

Achieving forecast credibility with local communities using modern climate science is a common challenge faced by scientific climate forecast producer globally. Currently, availability of and access to salient and integrated seasonal weather forecasts at community level for rainfed livelihoods, and the ability of traditional community users to interpret probabilistic climate information, is extremely inadequate. In the resulting uncertainty, conflicts can and do arise among communities in the process of adjusting to emerging weather situations.

In the absence of reliable conventional climate and weather information at community level, many local communities (peasant farmers, fishers, pastoralists, etc.) resort to indigenous and traditional knowledge of weather prediction, using local indicators, to bridge and fill the weather information gaps. Majority of local climate information users in fact trust traditional weather information knowledge more than conventional weather forecasts. However, climate change is impacting previously reliable local indicators of weather prediction through the disappearance or altering of the attributes of the indicators, making traditional weather forecasting less dependable as currently designed.

Conventional meteorological and hydrological service actors and agencies have in the past conducted pilots on forecast co-production and integration. However, the pilots are heavily inclined towards elderly male and mystical (secretive rainmaker) knowledge holders/ custodians in communities. Such pilots often merely ask subjective questions about whether traditional weather predictions correlate with conventional forecasts, and the questions never lead to any corresponding empirical comparison. The use of these two categories of the community for that purpose is not sustainable because individuals in this category and generation are phasing out due to natural attrition and modernity. The two models are neither testable nor replicable beyond the local community because there is no standard way to apply them across communities.

Ethnographic weather forecasts co-generated with local communities through consensus-based approaches have proven to simultaneously address the challenges of salience, access, legitimacy, equity, and integration of climate information services into service delivery. Generating locality-specific weather forecasts is known to enhance the capacity of smallholder crop growers, livestock producers, aquaculture practitioners, peasants, fishers, pastoralists and other stakeholders to use climate information to manage local climate risks. Such traditional methods of community level weather forecasting using authentic local experiences validated by community members will be more sustainable than the elderly male knowledge holder model and the mystical rainmaker model. The TILKIT tool provides an opportunity for empirical comparison between traditional and conventional weather forecast outcomes in terms of normal (historical average), below (dry or less) or above normal (wet or more) forecast probabilities.

### Challenges of climate change in the West Africa Region

The West Africa region, represented by the Economic Community of West African States (ECOWAS), faces a host of climate challenges, most critically droughts and changing rainfall patterns, leading to increased water scarcity, land degradation and reduced agro-pastoral productivity. The challenges have led to cases of cross-border movements in search of safety and better living conditions due to erratic rainfall, leading to conflicts. ECOWAS Climate Strategy and Action Plan (2022-2030) outlines measures to address the issues, in agriculture, livestock, fisheries, mobility, ecosystems, biodiversity, water, coastal zones, health, climate services, disaster risk management and early warning sectors among others. The Strategic aim is to transition ECOWAS towards a region resilient to climate impacts and vulnerabilities. The proposed TILKIT pilot will contribute to the ecosystem and biodiversity (indigenous indicators), climate services (early warning), water resources (rainfall forecasts), disaster risk management (advisories) and mobility (action planning) objectives of the Strategy.

## Geographic location:

### The tri-border area of Burkina Faso, Côte d'Ivoire, and Ghana

ECOWAS wishes to pilot TILKIT in the with a community in the tri-border area of Burkina Faso, Cote d’Ivoire and Ghana (Figure 1). The area is a space of vibrant cross-border interactions but faces significant challenges related to displacement and conflict. The variation in onset and cessation months is currently influenced by climate change. One primary driver for migration in the selected location is the one cropping season per year. Both crop farmers and pastoralists move out of the area during the long dry season and return when the rains start in either late April or early May. Among the communities traversing this tri-border area are the Koanta, kpere (Burkina Faso), Ivory coast: Tantama, varbo, Batipor, Doguina, Tagadi (Cote d’Ivoire) and Saru, Kluajon, kalba, konfusi, Dorimon (Ghana) among others. Each community has its unique cultural practices, but they all engage in various livelihoods and economic activities such as crop farming, livestock rearing, pastoralism, transhumance and trade. The communities are highly vulnerable to the impacts of climate change and increased climate and weather variability.

Figure 1: Project site - the tri-border area of Burkina Faso, Cote d’Ivoire and Ghana

The cross-border influx of people puts pressure on local economies, leading to resource competition and increased tensions, especially between nomadic herders and settled host communities. Competition over access to water and pasture has intensified, especially between pastoralist and transhumant communities (often from Burkina Faso) and farming communities in Ghana and Côte d’Ivoire. Pressures of climate change has intensified this competition, as erratic rainfall reduces the availability of farmland and grazing areas, leading to increased cross-border movement, displacement, and conflict in recent years. Addressing the root causes and drivers of displacement and conflict, such as climate change among others, is essential for long-term solutions. Investing in collaborative and consultative community-oriented approaches such as the TILKIT methodology to exchange knowledge and share information can promote social cohesion, strengthen resilience and reduce intercommunity conflicts.

SPECIFIC LOCALITY OF FOCUS: Due to budget constraints, the initial pilot will focus on the Ghana side in the tri-border region while paying attention to aspects of cross border practice and tradition. The main host communities to work with will be the Saru, Kluajon, Kalba and Konfusi. The cross-border consideration will help to anticipate future scaling approaches, which will then be reflected in the recommendations for further work. Based on the lessons of the pilot and the recommendations made, we can then explore how this could be expanded – i.e., targeting forums again, like the annual meeting of Directors of National Meteorology/ Hydrology institutes or other policy and development spaces.

# Profile of Implementing Partners - Presentation of the recipient

## Adaptation Consortium Registered Trustees

The Adaptation Consortium (ADA, https://adaconsortium.org/) is a partnership of like-minded national and international NGOs working closely with national government agencies, sub national government units and local communities to mainstream climate action into community-driven resilience programming, integration and institutionalisation. The aim is to promote locally led adaptation (LLA) and direct climate finance (DCF) through Community-based Adaptation (CbA) models. ADA started as a community resilience programme-support in 2013 but later converted into a legally registered Trust in 2021. Between 2013 and 2020, the consortium operated through an MoU signed between Kenya’s National Drought Management Authority (NDMA) and the International Institute for Environment and Development (IIED). ADA has a national-level secretariat based in Nairobi which provides technical and coordination support between members and external partners/ collaborators. ADA secretariat supports sub national government units to develop innovative mechanisms for accessing climate finance.

The partner NGOs in the consortium are spread across Kenya and largely working in the areas of climate change, environmental sustainability and social protection. They include but not limited to: Arid Lands Development Focus (ALDEF), Anglican Development Services Eastern (ADSE), Anglican Development Services Western (ADSW), Womankind Kenya (WOKIKE) and Merti Integrated Development Programme (MID-P) with offices in four of Kenya’s six regional economic blocs. Among the government partner departments and agencies are the Council of Governors (CoG), Climate Change Directorate (CCD), the National Treasury (TNT), National Drought Management Authority (NDMA), the Kenya Meteorological Department (KMD) and the Kenya School of Government (KSG).

## Climate and Environment Services

Climate and Environment Services (CES, https://ces-global.org/) is a not-for-profit organization, with a Headquarters in Accra Ghana, that undertakes research, consultancy and training to influence a sustainable world that benefits all, especially the poor and vulnerable. CES was born out of the need to translate climate and environmental knowledge into practice for sustainable development for all. CES Ghana is focused on advancing climate & environmental sustainability, especially on vulnerable communities. CES provides evidence-based research and capacity-building programs to support climate adaptation, disaster risk reduction, and sustainable development. Through innovation and strong partnerships, CES empowers communities and institutions with actionable climate information and solutions. CES researchers have worked on several projects that combine indigenous and scientific forecasts for water management and food production in West Africa and South Asia.

# Project objective/outcome:

The project aims to strengthen the climate resilience and adaptive capacity of vulnerable communities in the tri-border area of Burkina Faso, Côte d’Ivoire, and Ghana by piloting a Traditional, Indigenous and Local Knowledge Indicator Tool (TILKIT) for community-based weather forecasting. Through participatory co-development of localized climate services and anticipatory action plans, the project seeks to reduce climate-induced mobility, displacement, and conflict risks. The proposal outlines a few benefits that can directly enhance positive outcomes: -

| Area | Positive Impact |
| --- | --- |
| Livelihoods | More accurate, consensus-based forecasts reduce livelihood disruptions |
| Social Cohesion | Reduced displacement and conflict through co-produced advisory and planning that increases understanding and mutual respect |
| Local Knowledge Systems | Preservation and validation of indigenous forecasting strengthens cultural resilience |
| Governance | Integrating TILKIT into formal climate services fosters decentralized decision-making |
| Feedback & Adaptation | Learning-based adjustments ensure relevance and long-term usability |

### The proposed pilot project:

Local weather forecast scenario planning (to unpack uncertainty in seasonal forecasts) and weather advisory development is a valuable decision-making process for adaptation and resilience. The pilot project is proposed to run for 12 months from September/October 2025 and end in September/October 2026, covering one rainy season and one dry period. One primary driver of migration in the selected location is the cropping season. Both farmers and pastoralists move around during the dry season and return when the rains begin. This proposal emphasizes transdisciplinary co-production, monitoring and communication of local weather forecasts and weather advisories using consensus-based ethnographic weather indicators to bridge extant weather forecast gaps. The bridging covers gaps in disciplinary mix, production, language, interpretation, scales (spatial and temporal), technology transfer, forecast legitimacy and practical application among others.

The proposed project is to pilot TILKIT with selected communities on the Ghana side of the Burkina Faso-Côte d’Ivoire-Ghana tri-border area in the context of climate-induced human mobility, migration, displacement and conflict. The main aim of the project is to equip communities with a local weather forecasting tool and know-how (capacity building) to locally self-organise, co-generate and integrate a bottom-up traditional weather forecast into a top-down climate information. Lessons from the pilot will be integrated into broader scaling programmes within and beyond the Region.

### Project Objectives

The broad objective of the pilot is to enhance gender-responsive adaptive capacity, strengthen resilience and reduce vulnerability of target communities in the tri-border area of Burkina Faso, Cote D’Ivoire and Ghana in the context of human mobility, displacement and conflict. Gender equity and social inclusion (GESI) will ensure women and youth participation in community committees, training, and forecast validation, etc. The project will ensure active participation of women and youth in community committees, training, and forecast validation, recognizing their knowledge and roles as agents of change. Specific objectives are:

- To co-develop gender-responsive consensus-based decision-relevant seasonal weather forecasts, user-responsive, locally actionable weather risk and uncertainty advisories and Anticipatory action plans for enhanced resilience in the tri-border area of Burkina Faso, Cote D’Ivoire and Ghana

- To co-establish a gender-responsive climate information dissemination strategy and communication framework that respects, reviews and combines knowledge from local actors, including communities and service providers

- To co-facilitate and co-support communities and actors to implement the co-developed climate-informed gender-responsive anticipatory action plans to enhance climate resilience in all livelihoods, sectors, and development processes at the local level

- To share lessons from the gender-responsive process for wider consideration and policy dialogue to seasonally co-develop climate information services that are responsive to users’ changing decision-making contexts

# Expected Results

Project activities, indicators and expected results (outputs and outcomes) are summarized in the LogFrame (Log Frame) under Monitoring and Evaluation.  The results will contribute to the ECOWAS Climate Strategy and Action Plan (2022-2030) expected results in agriculture, livestock, mobility, ecosystems, biodiversity, water, health, climate services, disaster risk management and early warning sectors among others. Specifically, the pilot will contribute to the ecosystem and biodiversity (indigenous indicators), climate services (early warning), water resources (rainfall forecasts), disaster risk management (advisories) and mobility (action planning) objectives of the Strategy.

# Progress and Milestones

The pilot is too short for major milestones to be realistically achieved. However, we will document and report all progress made. In documenting and reporting progress, we will consider seasonality, regional context and flexibility. The project focuses on seasonal forecasting. Progress reports will need to reflect this, with key activities occurring before and during the two target seasons (e.g., rainy and dry).

# Approach and Methodology: planned activities for the implementation of the measures:

## Approach

Environmental monitoring, climate information and weather forecasts are powerful early warning tools required by local communities for local planning, risk management and disaster risk reduction. The project will cover one rainy season and one dry period in the proposed area, a duration of six months each, total 12 months, to pilot TILKIT for local weather forecasting and advisory development to support decision-making by local communities and indigenous peoples. Integrating TILKIT with scientific weather forecasts will lead to opportunities for climate scientists, local communities and indigenous peoples to anticipate shocks or risks and plan to counter them. The anticipatory action planning will be achieved by co-developing forecast products (forecasts, advisories and action plans) and co-designing action plans and dissemination of these products/advisories to the local communities. The team will then evaluate how decision-making agencies, and local communities integrate locally relevant prediction and indicators to improve on the contemporary weather forecast and predictions.

This approach is well placed to ensure that the outcomes of the project influence change to the nature of information that local communities and indigenous peoples receive and use. This will improve mobility plans and reduce forced displacement and resource-based conflict. Through co-production and dialogues, the team will explore how decision-making bodies need data/ information to be structured to respond to climate shocks and allow them to decide what information can enable local communities to make better decisions for their situation. Local service providers and intermediary organisations will be mobilised at the TILKIT workshop and after to support the implementation of the community anticipatory action plan.

The project will address three connected output areas i) strengthen the capability of local communities and indigenous peoples through adoption of TILKIT to co-produce weather forecasts, develop weather advisories and anticipatory action plans; ii) pilot the co-produced anticipatory action plans across one dry period and one rainy season and iii) dialogue on the pilot outcome to influence policy reforms and decision-making processes at multiple levels. The project will use three Work Streams or Phases to deliver the project objectives, and a fourth Work Stream or Component for project management and coordination.

### The TILKIT Workshop

The first Phase is adoption of TILKIT to co-produce weather forecast scenarios and anticipatory action planning. TILKIT is a methodological tool used to work with communities to co-produce weather forecasts and to plan based on the forecasts. The Tool is a way to empower communities to engage in CbA and sector planning while also safeguarding their rights through a “whole-of-society” approach. The approach includes co-designing, co-producing and co-guiding the activity planning process with communities. Evidence from this work will be packaged for sensitization to influence policy reforms and decision-making at various levels among relevant stakeholders in the region. The Tool is based on the belief that it is possible to build a new set of traditional knowledge using a new tool by opening the traditional conversation with the whole community (instead of just a select special few) to pick emerging indicators and experiences. The approach will use Focus Group Discussions (FGD) for different categories of community members to discuss and validate FGD results in plenary for community ownership of the outcomes. Participants will be divided into two or three groups-based on attributes such as gender, and the gender attributes will be nested with livelihoods and localities.

### The tri-border area pilot

The second Phase will pilot the co-produced local weather anticipatory action plan across one rainy season and one dry period (12 months). Activities under this Phase will i) evaluate how targeted end users interact and benefit from the co-produced forecasts/ advisories/ action plans, ii) identify behaviour mechanisms at different levels to promote the engagement of critical actors to foster utilization of the co-produced products (forecasts, advisories and action plans), iii) co-design information dissemination and service delivery mechanisms and tools to reach local and indigenous communities and iv) draw lessons from the application and use of such forecasts, advisories and action plans at the local level to influence the existing contemporary early warning services.

### Monitoring, sharing and learning

The third Phase will focus on monitoring and learning where evidence from the first two Phases can be packaged to influence policy reforms at various levels and among relevant stakeholders in the region. This will unpack what is being delivered, what is and is not working, why and how and deploy customized monitoring tools to co-assess changes in beneficiary/ end-user behaviour. Efforts will be made to explore opportunities for a central digital repository for all TILKIT weather forecasts to enable coordinated anticipatory action.

### Dissemination

To maximize the impact of the outputs the project will develop a dissemination plan for sharing project outputs and the emerging knowledge, data, and advisory services. The plan will bring together components across all project activities to ensure the project has high impact. The dissemination plan will include conventional and traditional delivery models as appropriate, e.g., journals articles, data portals, model exchange portals, conferences/workshops), relevant knowledge products such as practice briefs, policy briefs, etc.) as well as key messages of impacts achieved. It will also include capturing and disseminating best practices (through relevant websites, blogs, social media, journal articles, etc.) and sharing of such products via climate innovation platforms / multi-stakeholder platforms.

### Project management, coordination and partnership and roles

This work stream or component will support project management and coordination functions. ADA as the Lead implementer will hold ultimate responsibility for technical, administrative, fiduciary, legal, and safeguards compliance functions. ADA will not transfer funds to any partner on the ground but will work with partners based in Ghana for day-to-day responsibilities of the pilot facilitated by ADA. ADA’s partners in Ghana will provide site level oversight of the technical and backstopping activities, and coordinate the involvement of intermediaries on the ground to ensure site level collaboration among and between the local actors and stakeholders. ADA’s Ghana partners and local intermediaries will be mandated to disseminate the forecast products, advisories and action plans and to manage the pilot on the ground through stakeholder engagement. The partners will also supervise indicator monitoring activities and compile consolidated monitoring reports documenting progress achieved.

The team will also collaborate with national meteorological agencies in the region and other downstream partners and collaborators in the tri-border area to chart a course for TILKIT policy support. Collaborators will include but may not be limited to international organisations working in the project area, or the departments and agencies of the host governments in the country of implementation. Downstream partners will mainly be user-facing intermediary organisations responsible for frontline interventions with end users. There have been consultations with ADA’s Ghana partners in the past. Additional consultations will take place prior to project commencement. Regular consultations and stakeholder engagement will also occur before and during project implementation. Stakeholder engagement activities will include dialogues with multiple actors including policy makers, implementation managers, and field workers. The project team through the national project partners, will work with community groups through their identified intermediary organisations. Other activities will include dissemination of information through multiple media, evaluation of experiences during piloting to identify what works, and workshops to share experiences and obtain stakeholder buy-in. A summary of this section is provided in the following bullet points: -

- ADA: Project Lead – Overall project management and coordination and reporting

- Responsible for financial, legal and administrative management of the pilot

- Support the convening of learning events, training workshops, dialogue meetings, etc., at the national and local level in the respective country

- Backstop, jointly with Ghana partners, the national and local stakeholder events, including field level monitoring of implementation activities

- Other responsibilities as may arise from the above bullet points

## Methodology

Climate and environmental scientists in Eastern Africa*** and Ghana** have separately developed a tool, a Framework and a methodology for traditional forecasting of local weather by beneficiary communities which can be compared and complemented with conventional weather forecasting. A graphical representation of the TILKIT workshop model is illustrated in Figure 2, adapted from the Maastricht Report (unpublished). The steps of the TILKIT process are presented in Figure 3 and in the subsequent bullet statements.

Figure 2: A graphical representation of the TILKIT workshop model

Source: adapted from the Maastricht Report

Figure 3: Steps of the TILKIT process

Source: proposal authors

- Pre-Season or Pre-Workshop Planning: Literature review of project documents and relevant reports and articles to capture the context of each target community and each target region of the tri-border area. Initial identification of local level participants to train as trainers (ToTs). The ToTs will be trained to mobilize communities to collect TILKIT data for consideration during the workshop

- Inception meetings

  - Partnerships, stakeholder mapping and discussion on issues like cultural sensitivity & local adaptation, community ownership, collaboration & institutionalization, etc.

  - Contextualizing TILKIT to the target communities

- Training of Trainers and Community Indicator data Collectors.

  - Training and data gathering/ data collection/ data interpretation -

    - Community Plenary (introduction and training), Focus Group Discussion (FGD data gathering), Plenary (feedback, indicator validation and consensus building)

- The TILKIT Community Workshop - facilitated by experts and intermediaries (ToTs) at the community level or a cluster of communities

    - Top-down regional meteorological observations trickle down from national government to sub national units to intermediaries to communities

    - Simultaneously, bottom-up traditional and indigenous local observations are co-generated by community representatives facilitated by experts and intermediaries - impact forecasting

    - The two are integrated and harmonized to produce a consensus forecast upon which anticipatory action planning is premised - Integrated Consensus Forecasting

  - Data analysis and synthesis, development of forecast scenarios, scenario advisories and Anticipatory Scenario Action Plans (ASAP)

- Piloting/ implementation of Anticipatory Scenario Action Plans (ASAP)/ TILKIT application

- Monitoring, Evaluation and Learning

  - Data gathering/ information dissemination and early warning: communication channels, and intervals for community meetings

- Interviews with various local stakeholders

  - Solicitation of stakeholder views on the preservation and conservation of identified valuable TILKIT (environmental) knowledge indicators as a biodiversity action to enhance their continued use for posterity

  - Interviews on the quality assurance measures that are needed for credibility of the data generated, and how similarities and differences should be treated, including whether different indicators should be weighted to reflect their impact or they should all be accorded equal significance

  - Interviews on the kind of repository for the TILKIT data, knowledge and information, a repository accessible to users (e.g., interactive digital GIS maps)

# Criteria for selecting project participants and local stakeholders:

The target group is the communities within the tri-border area of Burkina Faso, Cote d’Ivoire, and Ghana, with a significant presence of displaced populations. Focus of the activities will be on the Ghana side of the tri-border area but with consideration of participants from the other two countries residing on the Ghana side at the time. The proposed intervention will purpose to work with the following groups of stakeholders, all of whom are relevant to the cross-border mobility, displacement and conflict nexus, as follows: -

- Transhumant and pastoralist communities

- Farming communities

- Communities members with strong indigenous and traditional knowledge systems in weather forecasting and climate adaptation, high vulnerability to climate change, and ongoing displacement or mobility challenges

- National and subnational government agencies, local civil society organizations, and academia in Burkina Faso, Cote d’Ivoire, and Ghana; including NGOs, faith based and communities, etc.

# Sustainability Plan, Exit Strategy and Scaling Roadmap

## Sustainability Plan

This project envisions TILKIT as a foundational approach for advancing localized, participatory, and inclusive climate services. The long-term goal is to institutionalize the tool across Africa’s climate-vulnerable regions as a sustainable model for integrating traditional knowledge into formal weather and early warning systems. The ultimate aim of TILKIT is to anchor resilience building in traditional knowledge systems, participatory planning, and community decision-making, thereby strengthening local climate governance and reducing climate-induced displacement risks. The TILKIT model aligns with ECOWAS Climate Strategy (2022–2030) and the African Union (AU) Agenda 2063 and, therefore, has the potential to evolve into a continental approach for climate-smart governance and anticipatory action planning. Sustainability for project outcomes will be addressed through institutional integration, community organisation, technical training and policy alignment.

Policy Integration: To secure TILKIT in ECOWAS Regio beyond the pilot, it will need to be institutionalized across three layers: local governance, climate service systems, and regional policy platforms. The implementing partners will work closely with national meteorological and hydrological agencies to embed the tool in their weather forecast integration processes, resilience strategies, early warning systems and action plans. These agencies will be engaged to adopt TILKIT as a complementary source of local weather data to enrich scientific forecasts. Joint activities will include seasonal planning sessions, data harmonization, validation workshops, and advisory production. Lessons and evidence from the pilot will be packaged to influence policy reforms and decision-making processes at various levels, from local to regional level. Integration will include co-developing operational procedures and institutional guidelines and aligning with national adaptation frameworks (especially those tied to ECOWAS and AU, e.g., mobility, disaster risk management, early warning, etc.). The outcome evidence will be presented at relevant AU thematic forums.

Institutional Integration: This will involve anchoring and embedding TILKIT in institutional structures post-pilot. The project team will work closely with local government institutions and community structures, relevant government agencies and local climate service units at the local level to embed the TILKIT tool in the local institutional systems which comprise communities and local intermediary institutions and organisations. The community structures put in place such as local coordination committees and local data collection groups will ensure operational continuity. The embedding will need to be escalated to national institutional frameworks and curricular through partnerships with academia and others.

Capacity Development: The project will train a cohort of local trainers (ToTs), TILKIT indicator monitoring groups in each pilot location as TILKIT Champions, forming a grassroots technical cohort for ongoing forecast co-production and action planning. These groups will continue collecting, validating, and interpreting local environmental indicators and traditional forecasting knowledge, sustaining the application of TILKIT at the grassroots level. The trained resource persons will be mobilised into local level TILKIT coordination committees to work closely with the local government administrators or local social centres in place. The project will equip communities with local weather forecasting tools and know-how to empower them to self-organize and co-generate traditional weather forecasts for integration with scientific weather forecasts. Feedback loops through seasonal reviews will adapt and refine emerging lessons for evolving local contexts. Local CSOs and intermediary organisations will be trained to continue facilitating TILKIT workshops, engaging with communities, updating forecasts, and supporting implementation of anticipatory action plans. Their role will include mobilization, training, information dissemination, and technical backstopping of TILKIT committees and community action plans.

Digital Repository: The implementing partners will explore opportunities for developing a central a platform and a digital repository to store TILKIT data, openly accessible to users and interested parties. This will potentially be an interactive GIS platform and a GIS-enabled tool/ open-access portal for public use by beneficiary communities, local government agencies, disaster response units, and meteorological agencies.

## Exit Strategy

The TILKIT pilot directly aligns with and contributes to ECOWAS Vision 2050 and AU Agenda 2063 through inclusiveness and gender-responsive resilience-building interventions that strengthen local governance and reduce fragility. It also aligns with ECOWAS Climate Strategy and Action Plan (2022-2030) objectives in agriculture, livestock, mobility, ecosystems, biodiversity, water, health, climate services, disaster risk management, and early warning sectors. Lessons learned from the TILKIT pilot will therefore be shared with ECOWAS, AU and other regional and continental agencies for integration into broader regional policies, programs.

### Phased Transition to Local Ownership

The final few months of the project will prioritize a gradual handover of project activities to local actors. Responsibilities will be gradually shifted to trained community committees and local governments. The project team will collaborate with national meteorological agencies and other downstream partners to chart a course for TILKIT policy support. Training manuals and materials, data and documentation templates, reporting formats, and translated user guides will be shared with community committees, local government agents, and intermediary organization actors to ensure operational continuity. Local NGOs, CBOs and CSOs will be trained to mobilize funds to continue facilitation of workshops and updating forecast advisories

#### Pilot Consolidation (Final 3 Months of Project)

- Host stakeholder review and reflection workshops with Meteorology and Hydrology Agencies to prepare for exit

- Develop a Knowledge Package Toolkit (manuals, forecasts, action planning templates)

- Draft and validate policy briefs, technical briefs, and implementation toolkits.

#### Institutional Uptake

- Train extension officers and disaster response units to use TILKIT forecasts and advisories.

- Embed community TILKIT Committees into local governance and extension units

- Establish community information hubs (e.g., GIS-based tools, seasonal bulletin boards)

  - A central hub to receive and synthesizes data from various regions

## Replication & Scaling

The project aims to position the TILKIT tool for scale-up beyond the initial pilot area through evidence-based engagement, capacity development, and regional advocacy.

### Scaling Roadmap

#### Evidence Consolidation: Documentation and Knowledge Packaging

Pilot results will be synthesized into policy briefs, success stories, technical reports, training materials, and academic publications. These materials will be used to communicate the value of TILKIT and influence its uptake across relevant institutions and regions. This evidence base will inform regional policy engagement, policy dialogues and policy reforms.

#### Regional and Continental Policy Engagement and Policy Dialogues for Integration

Scaling is a key objective of the pilot, both institutionally (scaling up) and geographically (scaling out). To achieve this, the project holders will need to: -

- Embed TILKIT into ECOWAS programming under Climate Services, Mobility, and Disaster Risk thematic areas TILKIT as a standard LLA tool.

- Present progress, outcomes and lessons at regional stakeholder meetings and events (e.g., ECOWAS Hydromet Director’s Forums, AU Resilience Summits, meetings of climate services and DRR, climate resilience conferences, etc.).

- Embed TILKIT modules into academic curricula (e.g., KNUST climate resilience programs, etc.).

- Establish a regional community of practice for continuous learning and tool evolution

- Collaborate with AU DRM and Climate Services Working Groups to align with Agenda 2063.

#### Training of Experts in National and Regional Climate and Disaster Institutions

Relevant experts in key institutions such as national meteorological agencies and disaster risk management authorities will be trained on the application of TILKIT. Standard operating procedures and co-forecast data integration frameworks or protocols will be co-developed to enable institutional adoption and adaptation of the tool in various contexts. Options will be considered for mainstreaming TILKIT through embedding the tool into national early warning systems and community risk contingency plans.

#### Geographic Expansion Pathways

Subject to pilot results, stakeholder feedback and lessons generated, TILKIT will be adapted for expansion across the tri-border area and into other vulnerable regions within West Africa. This scaling will be informed by contextual analysis, stakeholder consultations, and demand from regional actors. It is anticipated that, based on the tri-border participants on the Ghana side, the model will be adapted for rollout on the Burkina Faso and Côte d’Ivoire sides of the tri-border area. Further expansion across West Africa will be explored through partnerships with regional technical institutions, ECOWAS, and African Union-affiliated agencies.

# Monitoring, evaluation and reporting

The TILKIT approach has a monitoring model embedded in real time local environmental monitoring of TILKIT indicators to track local scale weather. The model will be activated in the pilot. The model presents a valuable opportunity for hazard early warning and climate risk management and communication of local weather forecasts and weather advisories using consensus-based ethnographic weather indicators to bridge extant weather forecast gaps. The purpose is for practitioners, researchers and stakeholders to collect, preserve, calibrate, validate and adopt ITK indicators to integrate with conventional climate monitoring and weather forecasting to address residual climate risks that scientific forecasts alone might not cover. The third phase of this pilot will focus on monitoring and learning where evidence from the first two phases can be packaged to influence policy reforms at various levels and among relevant stakeholders in the region. This will unpack what is being delivered, what is and is not working, why and how and deploy customized monitoring tools to co-assess changes in beneficiary/ end-user behaviour. ADA and CES will jointly supervise monitoring and evaluation activities and compile consolidated monitoring reports documenting progress achieved.

M&E of Sustainability Impacts

| Area | Indicator | Method of Measurement |
| --- | --- | --- |
| Environmental Sustainability | Continued use and preservation of validated ITK indicators | Interviews, biodiversity conservation records |
| Social Sustainability | Participation of women and youth in forecasting and planning | Gender audits, FGD tracking, workshop registers |
| Institutional Sustainability | Number of agencies adopting TILKIT in planning | MOUs signed, integration in work plans |
| Forecast Impact | Improvement in livelihoods due to anticipatory actions | Household surveys, income tracking |
| Learning & Feedback | Number of documented refinements and adaptations | Policy briefs, monitoring reports |

### Project LogFrame

The Project LogFrame (Log Frame) is presented in Table 1.

Table 1: Project log frame

| Logic | Project summary | Indicators | Means of verification | Risks | Assumptions |
| --- | --- | --- | --- | --- | --- |
| Goal (Broad Objective): (Systemic, transformational impacts/ evidence-informed policy decisions) – Conditions (social, economic, environmental, civic, etc.) | Strengthen climate resilience and adaptive capacity of target communities in the tri-border area of Burkina Faso, Cote D’Ivoire and Ghana in the context of human mobility, displacement and conflict | Reduction in the number of households experiencing significant negative impacts from climate-related disasters (e.g., floods, droughts, extreme heat) in the tri-border area | Community surveys/ interviews/ Displacement records/ Livelihoods reports | Political instability and conflict may hinder project implementation and data collection/ Climate change impacts may be more severe than anticipated, exceeding the project's capacity to address them/ Limited access to and availability of reliable data on climate-related impacts and vulnerabilities | A secure and enabling environment will be maintained throughout the project implementation period/ The project's interventions will be adaptive and responsive to changing climate conditions/ Sufficient resources will be allocated for data collection, analysis, and dissemination |
| Project Objective (Impact or Cumulative, incremental Outcomes) – Action, behaviour, practice, decision-making, policies | To co-develop consensus-based decision-relevant weather forecast products (forecasts, advisories and action plans) for enhanced resilience in the tri-border area of Burkina Faso, Cote D’Ivoire and Ghana | Number of communities in the tri-border area with documented, locally-owned, and utilized consensus-based seasonal weather forecasts and corresponding anticipatory action plans | Documented forecasts and action plans/ Observation of plan implementation/ interviews/ discussions | Political instability and conflict may hinder project activities | Stable political environment and continuous support from local governments |
| Outcomes (Behaviour change) – e.g., Awareness, knowledge, attitudes, skills, opinions, aspirations, motivations | Enhanced community-based climate information systems and improved decision-making processes that integrate traditional and indigenous knowledge with scientific forecasts for climate-resilient livelihoods and reduced climate-related displacement risks | - Progress, findings, systems change, lessons, behaviour changes observed, knowledge products developed, local systems, institutions and structures established, policy makers engaged - Recommendations made - Percentage of households in target communities reporting improved decision-making related to climate risks based on the integration of traditional and indigenous knowledge (TILK) with scientific forecasts | Community surveys/ Focus group discussions/ Case studies/ Document reviews | Limited community participation and ownership of the climate information system/ Inadequate integration of TILK with scientific forecasts/ Limited access to and dissemination of climate information/ Lack of sustained support for the community-based climate information system | Adequate community engagement strategies will be implemented to ensure active participation and ownership/ Effective methodologies will be developed and implemented to facilitate the meaningful integration of TILK and scientific knowledge/ Effective communication channels will be established to ensure timely and accessible dissemination of climate information to target communities |
|  | Enhanced resilience in the tri-border area through improved decision-making based on relevant weather forecast products | Reduction in reported negative impacts of climate-related events on vulnerable populations in the tri-border area | Before-and-after comparisons | Inaccurate weather forecasts due to limited data | Access to accurate and comprehensive data for weather forecasting/ Mechanisms will be established to ensure the long-term sustainability of the system, including capacity building, resource mobilization, and local ownership |
| Outputs (Products and Services) | Locally-led and community-owned systems for co-producing and utilizing climate information, including Traditional Indigenous and Local Knowledge (TILK), for improved decision-making and reduced climate-related displacement risks | - Brief reports of activities implemented - Tools developed for further implementation - Numbers achieved (events, engagements, items, participants, systems, etc.) | Documentation of established systems, including membership rosters, meeting minutes, and reports on activities | Lack of community buy-in and engagement | Communities are willing to participate and contribute to the project |
|  | Consensus-based decision-relevant weather forecast products co-developed and piloted with user group | Number of locally-relevant weather forecast products co-developed and piloted | Reports detailing the co-developed forecast products, workshops proceedings, and pilot implementation feedback | Delay in developing weather forecast products | Timely completion of all planned activities and sufficient resources |
| Activities/ measures | Conduct a series of activities to co-develop and pilot a community-based climate information system utilizing the Traditional Indigenous and Local Knowledge Indicator Tool (TILKIT) method | - Customized, locally relevant Tools for implementation - Number of TILKIT workshops conducted and number of communities participating | Workshop attendance records, workshop reports, and documented evidence of community participation | Insufficient capacity of local partners to implement activities | Adequate resources and support will be provided to local partners |
|  | To co-develop consensus-based decision-relevant weather forecast products (forecasts, advisories, and action plans) using the Traditional Indigenous and Local Knowledge Indicator Tool (TILKIT) method | Number of consensus-based seasonal weather forecasts and corresponding anticipatory action plans developed and implemented through the TILKIT process | Documented seasonal forecasts/ Anticipatory action plans/ Implementation records/ Feedback and evaluation | Lack of cooperation from local communities and stakeholders | Active participation and collaboration from all stakeholders involved |

### Plan of activities/ Work plan/ Work Plan for one year

The details are found in Table 2 below.

Table 2: Planned activities

| Activities | Qter1 | Qter2 | Qter3 | Qter4 |
| --- | --- | --- | --- | --- |
| 1.1 Desktop/ literature/ document reviews, covering the tri-border area but focusing on a Ghana side implementation |  |  |  |  |
| 1.2 Convene inception meetings to establish partnerships, collaboration and consultative arrangements with tri-border, national and local actors to identify and onboard gender-responsive community representatives and local stakeholders |  |  |  |  |
| 1.3 Develop locally-relevant gender-responsive training materials, survey questionnaires and a template for documenting Traditional Indigenous and Local Knowledge Indicator Tool (TILKIT) observations |  |  |  |  |
| 1.4 Train trainers (ToTs) to conduct supervised gender-responsive TILKIT workshops per country for the three countries (Focus of this activity will be on the Ghana side of the tri-border area) |  |  |  |  |
| 1.5 Organize at least 1-2 (30-50pax) community-level TILKIT workshops on the Ghana side of the tri-border region for each of the two planned seasons to review and plan the season (Round_1 and Round_2) - to explore TILKIT scenarios and their implications for local livelihoods and gender-responsive actions |  |  |  |  |
| 1.6 Support establishment of local community gender-responsive TILKIT observation and action groups/ committees to oversee the piloting and monitor the progress of TILKIT anticipatory action plans while also tracking the performance of identified TILKIT indicators |  |  |  |  |
| 1.7 Develop and roll out a gender-responsive TILKIT weather forecast and Anticipatory Action Plan pilot, with technical support to track implementation during pilot, including feedback from beneficiaries (Round_1 and Round_2) |  |  |  |  |
| 1.8 Support the dissemination of the customized gender-responsive TILKIT actionable impact advisories and anticipatory action plans |  |  |  |  |
| 1.9 Convene stakeholder meetings to review and update or revise advisories and TILKIT anticipatory action plans based on new emerging data, stakeholder feedback, and lessons learned (aligned to gender-responsive Adaptive Management) |  |  |  |  |
| 2.1 Support the design and development of gender-responsive visual aids and simple language (& local, culturally appropriate, multilingual materials e.g., videos, audio, infographics) to communicate weather forecasts, warnings, and climate adaptation information |  |  |  |  |
| 2.2 Facilitate the convention of regular gender-responsive meetings of Local Communication Groups/ Committees to sustain the communication of the forecast and action plan, information and gather feedback through traditional and modern communication methods |  |  |  |  |
| 2.3 Support the organization and hosting of local gender-responsive communication campaigns/ events to raise understanding of weather information and decision-making processes |  |  |  |  |
| 3.1 Convene meetings to rally actors to mobilize resources (financial, technical, & material) needed to implement the gender-responsive pilot TILKIT anticipatory action plans |  |  |  |  |
| 3.2 Initiate meetings to facilitate the development and distribution of gender-responsive tools (e.g., weather indicator calendars ¦ cropping and grazing calendars ¦ hazard/ risk maps ¦ etc.) to inform TILKIT anticipatory decision-making |  |  |  |  |
| 3.3 Convene meetings to support national and sub national governments and communities to embed the TILKIT Tool into existing development plans and livelihood strategies in a gender-responsive manner |  |  |  |  |
| 3.4 Convene meetings to identify or develop a framework to provide access by communities to tools, technologies and resources (e.g., interactive maps) to enable informed implementation of TILKIT anticipatory actions in a gender-responsive manner |  |  |  |  |
| 3.5 Convene meetings to discuss technical support to local institutions to align their efforts with the TILKIT anticipatory action plans in a gender-responsive manner |  |  |  |  |
| 3.6 Organize field visits to backstop implementing communities and their intermediaries to regularly monitor traditional weather indicators and record actual indicator outcomes in a gender-responsive manner |  |  |  |  |
| 4.1 Compile and share through learning events (at local, national. regional and international workshops and conferences) reports that document the lessons learned, successful strategies, and challenges faced during the pilot project in a gender-responsive manner |  |  |  |  |
| 4.2 Organize at least one gender-responsive regional/ international learning event with policy makers to share lessons with decision makers |  |  |  |  |
| 4.3 Develop and present, in a gender-responsive manner, the “most significant outcome” stories that highlight the specific success instances to sustain momentum (in a workshop) |  |  |  |  |
| 4.4 Develop and present, in a gender-responsive manner, policy briefs and technical papers that summarize the key lessons and provide actionable recommendations for policymakers (in a workshop or meeting) |  |  |  |  |
| 4.5 Support (in a gender-responsive meeting) the setting up and popularizing community-based TILKIT weather forecast information hubs, preferably at the offices of the local level government administrators or community social centres, with requisite information tools and materials |  |  |  |  |
| 4.6 Conduct, in a gender-responsive manner, post-event stakeholder evaluations (workshop) to gather feedback and learn lessons for future improvements |  |  |  |  |
| 4.7 Disseminate, in a gender-responsive manner, findings in peer-reviewed journals and relevant publications to reach a wider academic and scientific audience (through write-shops, workshops, conferences) |  |  |  |  |

# Risk and damage limitation

We have identified a few risks which we present Table 2.

Table 3: Risk Matrix

| Risk Category |  | Risk Description | Probability | Impact | Risk Level | Risk Mitigation Strategies |
| --- | --- | --- | --- | --- | --- | --- |
| Project Level Risks | Political disruptions | Political disruptions in any of the target countries could disrupt project activities, hinder access to communities, and impact the safety of project personnel | High | Severe | High | We will build strong relationships with local authorities, and maintain flexibility in project implementation plans |
|  | Funding Constraints | Insufficient or delayed funding could lead to project delays, reduced scope, and the inability to achieve desired outcomes | Medium | Moderate | Medium | We will request implementing partners to take up some of the costs, and explore cost-effective solutions to some activities |
|  | Security Challenges | Security threats, such as terrorism, banditry, and inter-communal conflicts, could pose significant risks to project implementation and the safety of project staff and beneficiaries | High | Severe | High | We will collaborate with local security agencies, and prioritize safety and security measures for project personnel |
|  | Extreme weather events | Extreme weather events (droughts, floods) can disrupt project activities, impact target communities, and potentially derail project timelines | Medium | Moderate | Medium | This is the basis of the project, to build community resilience to natural disasters. We will therefore anticipate the possibility of extreme weather events and integrate weather risk reduction measures into project activities |
| Technical Risks | Data Quality Issues | Imprecise, inaccurate or incomplete data from traditional knowledge sources or meteorological services could lead to unreliable forecasts and ineffective anticipatory actions |  |  |  | We will ensure proper training for data collectors, adopt rigorous data quality control measures and conduct regular data validation checks |
| Social and Cultural Risks | Resistance to innovation | Resistance by experts to new approaches or skepticism towards traditional knowledge could hinder project implementation | Medium | Moderate | Medium | We will patiently explain the innovation and address expert concerns and anxieties |
|  | Gender Inequality | Unequal participation of women and youth in project activities, limited access to resources, and gender-based discrimination could undermine project effectiveness and sustainability | Medium | Moderate | Medium | We will ensure gender-sensitive project implementation, promote women and youth participation in all project activities, and address gender-based barriers to access and participation |
|  | Cultural Sensitivity | Failure to adequately address cultural sensitivities and local customs could lead to miscommunication, misunderstandings, and project failure | Medium | Moderate | Medium | We will conduct cultural assessments, ensure culturally appropriate communication and engagement strategies, and involve local cultural experts in project implementation |
| Implementation Risks | Delays in Project Activities | Delays in obtaining necessary approvals, could impact project timelines and budgets | Medium | Moderate | Medium | We will proactively address potential delays. We have developed realistic project timelines and established clear milestones |
|  | Inadequate Stakeholder Engagement | Insufficient stakeholder engagement and participation could lead to inadequate buy-in, limited ownership, and ultimately, project failure | High | Moderate | High | We will conduct regular stakeholder consultations and ensure active participation of all stakeholders |
|  | Communication Challenges | Poor communication and coordination among project partners and stakeholders could lead to confusion, duplication of efforts, and missed opportunities | Medium | Moderate | Medium | We will establish clear communication protocols, utilize multiple communication channels, and conduct regular communication audits |
| Monitoring and Evaluation Risks Monitoring and Evaluation Risks | Data Collection Challenges | Difficulties in monitoring traditional indicators could hinder the assessment of project progress and impact | Medium | Moderate | Medium | We will mount monitoring campaigns and conduct regular data checks to ensure reliable data collection and management |
|  | Insufficient Resources | Limited resources for monitoring and evaluation activities could compromise the quality and timeliness of data collection and analysis | Medium | Moderate | Medium | We will explore cost-effective monitoring methods, and leverage existing local intermediary support. |
|  | Inadequate community capacity | Insufficient capacity within the community to effectively monitor and learn from project activities could limit the ability to adapt and improve | Medium | Moderate | Medium | We will provide comprehensive training and capacity building for community reps in monitoring and evaluation methodologies and establish monitoring committees |

# References:

- ECOWAS Strategy and Action Plan

- Maastricht University and Climate Resilient Borderlands Horn of Africa (2024). Climate Resilience in the Karamoja Cluster: A Recommendations Report (Unpublished).

- Osumba J. (2022). Participation Report at the Biennial Africa Climate-Smart Agriculture Conference (FARA) in Ghana. AICCRA Conference Participation Report. Accelerating Impacts of CGIAR Climate Research for Africa (AICCRA). CGSpace, A Repository of Agricultural Research Outputs

- Osumba J., Ahlers M., and Makonnen B., (2023) How to weave local and indigenous knowledge in climate monitoring and weather forecasting in Africa. AICCRA Programme Blog. CGIAR

- Osumba J.J. L., Radeny M, Recha J.W., Oroma G.W, Nzoka O, Mbingo J, Warinda E, and Mwale S. (2023) Towards a Replicable Innovative Tool for Adaptive Climate Monitoring and Weather Forecasting Using Traditional Indigenous and Local Indicators to Strengthen Agro-Weather Resilience at Scale. FARA Research Report Vol 7(25):296-320.

- Osumba Joab J. L., (2020). Mainstreaming climate change response in Field School Methodology to strengthen climate-resilient service delivery. Selected practices. Digital Report of the Virtual Knowledge Share Fair held on 19th - 23rd October 2020

- Osumba Joab J. L., John W. Recha, and George W. Oroma (2021) Appendix A Table A1/ Box 1/ Box 2. Indigenous technical knowledge (ITK) local weather indicator monitoring and tracking tool. In: Transforming Agricultural Extension Service Delivery through Innovative Bottom–Up Climate-Resilient Agribusiness Farmer Field Schools. Sustainability 2021, 13(7), 3938

- Making Climate Services Actionable for Farmers in Ghana: The Value of Co-Production and Knowledge Integration Making Climate Services Actionable for Farmers in Ghana: The Value of Co-Production and Knowledge Integration | SpringerLink

- Techniques and skills of indigenous weather and seasonal climate forecast in Northern Ghana Full article: Techniques and skills of indigenous weather and seasonal climate forecast in Northern Ghana (tandfonline.com)

- Towards weather and climate services that integrate indigenous and scientific forecasts to improve forecast reliability and acceptability in Ghana Towards weather and climate services that integrate indigenous and scientific forecasts to improve forecast reliability and acceptability in Ghana - ScienceDirect

# Annexes

# 1 Feedback from the May 20 2025 ECOWAS Meteos (NMHSs) Meeting Pitching

| Clarification sought |  |  | Response given |
| --- | --- | --- | --- |
| - AGRHYMET (The Regional Climate Centre - RCC) =>: The AGRHYMET participant lauded the presentation as “very interesting” on how to integrate scientific and traditional forecasts, and added that this is a very important topic. The initiative is laudable, and needs to be discussed with a view to making progress on this aspect. But the participant raised two points of clarification which needed a response from the presenter on how to integrate the forecasts: - |  |  |  |
|  | - Before the merging of scientific and ITK forecasts, what is the scale of the information being merged? What is the relative scale of each of these forecasts? |  | - The scale is the same. Downscaled meteorological forecasts meet upscaled community ITK forecasts at the level of the sub national TILKIT workshop. The various community level forecasts are first merged to form a sub national level ITK forecast before the integration begins |
|  | - To avoid contradictions while navigating the various information sources, what are the sources of the various information that are used to determine the ITK forecasts? This is very important! |  | - In terms of sources, past approaches to ITK of local weather forecasting relied solely on elderly male and mystical (secretive rainmaker) knowledge holders/ custodians in communities. This model is being overtaken by events and therefore we saw the need to open the process to the whole traditional community (male, female, youthful and elderly and the rainmakers) for recalibration and validation, with the possibility of replication and scaling |
|  | - Operationalization - availability of an operational mechanism for ITK data collection on weather forecast indicators - how can we work around this? |  | - In the TILKIT process we work with all community members as “knowledge holders/ custodians” in a “whole-of-society” approach. The TILKIT process requires a consistent schedule for observations by the knowledge holders (e.g., daily, weekly, seasonal observation logs) based on the nature of the indicators. Community forums are convened by community coordinating committees (or Community Monitoring Teams) for reporting and data aggregation. Readily available communication methods are used to disseminate the emerging information and gather updates. |
|  |  | - What is observed at operational level in each locality (Village or Area)? | - What is observed at operational level is the behavior of ITK indicators of local weather in relation to their potential to predict rainfall or lack of rainfall. Community forums are convened to validate what is observed and the interpretation that is offered for them. |
|  |  | - How do you put in place a data collection network for this type of data? | - We go through intermediaries to identify local ITK knowledge holders/ custodians and champions and build their capacity in observation, documentation of relevant data using a template. Community forums are convened for validation and refinement to enhance legitimacy. We are thinking of digitizing the mechanism and linking directly with meteorological service platforms to make the documentation and reporting instant and to make the co-production more automatically integrated. However, that will depend on availability of funds |
|  | - Are there limitations? What limitations exist? |  | - There have been some limitations in the past which the TILKIT tool was designed to address, like aging and declining numbers of knowledge holders, the absence of a standard tool that can be applicable systematically across all situations in a “whole-of-society” approach, and the lack of empirical quantification for meaningful comparison and legitimate integration. For instance, most of the work done prior to our work was more of qualitative anthropological description of understanding ITK forecasts, with no quantitative data for comparison with scientific forecasts. We went a step further to make a case for the ITK forecast in a more quantitative way - collecting actual data using identified indicators and validating the observations through community triangulation. Some limitation still exists on the spatial coverage, the rigor, the quality of data and the community volunteer problem, but the process points to a strong beneficial effect on community acceptance of the outcomes. |
|  | - What is your comment on the fact that climate change is affecting indicators? What were the meanings of indicators in the past? Are the meanings still the same? What has changed? How do you address that? |  | - Those changes are the reasons we are opening the whole process and concept of ITK forecasting to the whole community for recalibration and validation to account for climate change and environmental change. Much as climate change and environmental change are affecting historical indicators, the same climate change is creating new indicators, which community members, especially women and youth, are observing. These community members have never been given a chance to describe what they are observing. TILKIT gives them that opportunity to track both the historical and emerging indicators, recalibrate and validate them. Apart from opening up the process to the whole-community approach, TILKIT also gives life to inter-generational understanding of the indicators, from elders to women and youth, and from disappearing historical to emerging new indicators |
| - NIGERIA: The Nigerian participant pointed out that he has tried in the past with how to introduce science into what Traditional Rainmakers do, and expressed interest in looking at the work done about the current methods from Kenya and Ghana to compare. |  |  | We are equally grappling with the climate science behind what Traditional Rainmakers do, and we will continue to work together on this |
| - ACMAD: The ACMAD participant expressed the need to document ITK of weather forecasting in Western Africa as has been done in Eastern and Southern Africa, to preserve the knowledge for posterity. |  |  |  |
|  | - The knowledge needs documenting at all levels, starting from the community, with a baseline to be a reference point. |  | - The proposed pilot is a good starting point for such a documentation. If funds allow, the suggested reference baseline can be generated in the life of this pilot. |
|  | - We need to get academicians, communities and meteorological service agencies to be involved in this work, since it is these agencies that have authoritative voices with the mandate to report the outcomes |  | - These stakeholders will all be included in the Stakeholder Engagement Plan and be involved in the pilot |
|  | - We have communities where individuals have been recording rainfall since 1980s - just recording the fact that it rained on a particular day, and indicating the perception of scenario, e.g., heavy, light or moderate. |  | - This is laudable, and the champions need to be identified and included in this process |
|  | - The ADA Consortium and CES, with ECOWAS and the Regional Climate Center (RCC) AGRHYMET, etc., ACMAD will be willing to participate to quickly generate literature for the West Africa Region |  | - The interest is registered and will be tapped |
| - ???? (We didn’t quite get this pronunciation well!): This method is looking more advanced than what we have been doing with ITK forecast integration so far. Whenever we talk about indigenous or local forecasting, we mainly base our views on the empirical science of the indicators e.g., floral changes. This method goes beyond that, to capture and document other aspects not considered in the past. In conventional forecasting we determine the start and end of seasons based on various forecasting mechanisms. |  |  |  |
|  | - I would like to know the mechanisms used, under TILKIT, to identify agrometeorological parameters |  | - As both climate and environment changes the indicators also need to be recalibrated and re-weighted. Due to strong interest, we can see how best to approach it. |
|  | - Can we use conventional forecasting to check and verify whether they are reliable? How can Meteo Methods be used to verify ITK of forecasts? |  | - In Ghana they have also attempted to assign value to each indicator - In Kenya, ICPAC said we need to consider confidence level and assign a weighted index of “confidence level” to each indicator based on the confirmed reliability level post-season, to help recalibrate the indicators for the next season. |
| - WMO - A question on the demarcations: You have indicated that in Kenya the ITK forecast is at community level while the meteorological forecast is downscaled up to sub national level. This is where I don’t get the understanding clearly - How are the two integrated? |  |  | The scientific forecast is downscaled to county level while community ITK forecast is upscaled to county level before the integration is done |

How to weave local and indigenous knowledge in climate monitoring and weather forecasting in Africa https://aiccra.cgiar.org/news/how-weave-local-and-indigenous-knowledge-climate-monitoring-and-weather-forecasting-africa

Towards a Rights-based Innovative Traditional Knowledge Tool for Systematic Weather Forecasting and Decision Support by Indigenous and Local Communities https://www.cemiride.org/traditional-weather-forecasting-policy-brief/

Maastricht University and Climate Resilient Borderlands Horn of Africa (2024). Climate Resilience in the Karamoja Cluster: A Recommendations Report (Unpublished)

An Economic Valuation of the Kenya Meteorological Department’s Decentralised Provision https://www.iied.org/22066g

ITK has been used to forecast local weather in very many contexts around the world, including human mobility contexts, but a systematic approach has never been designed and applied

Such indicators may include biological (behaviour of plants, animals), ecological (behaviour of ecosystems, etc.), physical (behaviour of objects and materials, position and motion of objects, water-related features e.g., dew, etc.), sky: astrological, astronomical or celestial features (behaviour of whirlwinds, clouds, moon, stars, etc.), behaviour of the human body (sensations), etc., all of which are validated through observation and monitoring

The concept of Indigenous knowledge is now understood to go beyond the narrow interpretation to include traditional and contextual knowledge of local and indigenous communities, encompassing cultural knowledge in its broadest sense, including all of the social, political, economic, and spiritual aspects of a local way of life.

Such indicators may include biological (behaviour of plants, animals), ecological (behaviour of ecosystems, etc.), physical (behaviour of objects and materials, position and motion of objects, water-related features e.g., dew, etc.), celestial or astrological features (behaviour of whirlwinds, moon, etc.), behaviour of the human body (sensations), etc., all of which are validated through observation and monitoring

Mystical: secretive ritualistic rainmaking (magical, supernatural, spiritual) practices.

Due to budget constraints, the initial pilot will focus on the Ghana side in the tri-border region while paying attention to aspects of cross border practice and tradition. The cross-border consideration will help to anticipate future scaling approaches, which will then be reflected in the recommendations for further work. Based on the lessons of the pilot and the recommendations made, we can then explore how this could be expanded – i.e., targeting forums again, like the annual meeting of Directors of National Meterology/Hydrology institutes or other policy and development spaces.

West and Central Africa — Transhumance Tracking Tool — Mapping of Herders Stranded Along the Central Transhumance Corridor (January 2021)

Elodie Maitre d’Hôtel et al. (2023). Resilience of food system actors to armed conflicts: empirical insights from Burkina Faso.

KAPOK Project - Peace Initiatives in the Border Region of Côte d'Ivoire, Burkina Faso, and Ghana: Strengthening resilience against violence and conflict in the Sahel region

Principles for locally led adaptation https://www.iied.org/principles-for-locally-led-adaptation / https://www.wri.org/initiatives/locally-led-adaptation/principles-locally-led-adaptation

WMO/GFCS/ NFCS/ NMHS supports the adoption of co-production of climate services at the national and sub-national level in line with available guidelines

Transdisciplinary co-production, monitoring and communication of local weather forecasts and agro-weather advisories using consensus-based ethnographic weather indicators

ADA’s partners in Ghana include traditional weather forecasting experts at Climate and Environment Services (CES) and Kwame Nkrumah University of Science and Technology (KNUST, Ghana)

Transforming Agricultural Extension Service Delivery through Innovative Bottom–Up Climate-Resilient Agribusiness Farmer Field Schools https://www.mdpi.com/2071-1050/13/7/3938

Participation Report at the Biennial Africa Climate-Smart Agriculture Conference (FARA) in Ghana Participation Report at the Biennial Africa Climate-Smart Agriculture Conference (FARA) in Ghana (cgiar.org)

How to weave local and indigenous knowledge in climate monitoring and weather forecasting in Africa https://aiccra.cgiar.org/news/how-weave-local-and-indigenous-knowledge-climate-monitoring-and-weather-forecasting-africa

Towards a Replicable Innovative Tool for Adaptive Climate Monitoring and Weather Forecasting Using Traditional Indigenous and Local Indicators to Strengthen Agro-Weather Resilience at Scale https://library.faraafrica.org/2023/04/26/towards-a-replicable-innovative-tool-for-adaptive-climate-monitoring-and-weather-forecasting-using-traditional-indigenous-and-local-indicators-to-strengthen-agro-weather-resilience-at-scale/

Making Climate Services Actionable for Farmers in Ghana: The Value of Co-

Production and Knowledge Integration Making Climate Services Actionable for Farmers in Ghana: The Value of Co-Production and Knowledge Integration | SpringerLink

Techniques and skills of indigenous weather and seasonal climate forecast in Northern Ghana Full article: Techniques and skills of indigenous weather and seasonal climate forecast in Northern Ghana (tandfonline.com)

Towards weather and climate services that integrate indigenous and scientific forecasts to improve forecast reliability and acceptability in Ghana Towards weather and climate services that integrate indigenous and scientific forecasts to improve forecast reliability and acceptability in Ghana - ScienceDirect

Maastricht University and Climate Resilient Borderlands Horn of Africa (2024). Climate Resilience in the Karamoja Cluster: A Recommendations Report (Unpublished)

TILKIT Outputs: List of indigenous indicators/ and what they signify; Forecast; Scenarios; adaptation strategies; Advisories; Anticipatory Action Plans; Dissemination and Communication Plans; Monitoring and reporting plans; Policy dialogue plans, etc.

Mystical: secretive ritualistic rainmaking (magical, supernatural, spiritual) practices.